## Sheet1
				Guilherme
Home Page				Product Page				Carlota
(Guilherme)				(Guilherme)				Christian
1. Load data from JSON				1. Get data form URL (GET)
2. Design				2. Fill all data
3. Print products				3. Adapt new header (include)
4. Listener on click, redirect to product
5. Add include for header

Refactor Validate				Save Data
(Christian)
1. Send info with POST (JS)				1. Receive data
2. Recover info (PHP)				2. Store data
3. Validate info (PHP)
4. Send info + current step (PHP)
5. Send response to JS (PHP)
6. Receive resp. and continue form (JS)

Admin				Fix errors
				(Guilherme)
Login (admins.json)			(Login: falta hacer la comprobacion por JSON)	No max time
Modify products (products.json)				Placeholder contraseña
Modify product				Radio buttons
Delete product				General design
Add product (name, id, size, colors)				Progress bar (center)
Modify Admins (create/delete)				Inline styles in product.php
				Reform id/class in product html

## Sheet2
	Monday	Tuesday	Wednesday	Thursday	Weekend (4-5 of July)
Carlota	- AdminValidations PHP / - Log in/ Sign out / - Products (Add/Update) / - Users(Add/Update)	- Finish validation new user. / - Validation of new products. / - Function of search bar of products and admins. / files .php of update products and admins.	- Add one to the admin and product ID / - Finish validation new product / - Print the validation data in the update table (user and product) / - Delete function (product and user)
Guilherme	-Pass "id" variable to JS with / get-product.php and eliminate "id" / property from catalog.json / -Create home-page HTML structure	- Help Carlota with Admin / - Work on home-page style / - Work on product-page first step style / - Fix placeholders	- Work on step 4 styles (responsive) / - Eliminate all HTML inline styles / - Fix buy timeout function (major problem) / - Insert a footer on home-page		- Changed images to assets/img/products folder. / - Created product images pattern ("id"-"colorName"-"photoNumber".jpg). / - Created a new product (id = 1). / - Added "id" property to products in catalog.json file. / - Added php script on product page to check if the GET method was made. / - Created get-product.php file to filter selected product in catalog.json file. / - Added code to script.js to request product info to get-product.php file and fill page with products info. / (All Guilherme!)
Christian	- Send info with POST (JS) / - Validate info (PHP) / - Send response to JS (PHP) / - Receive response and proceed / with form (JS)	- Send info with POST (JS) / - Validate info (PHP) / - Send response to JS (PHP) / - Receive response and proceed with form (JS)	- Store form data in leads.json / - Load from data from lead.json if any
Àlex	- 404 Page / - Back Soldier	- Readme.md / - PDF documentation / - 404 page